## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JL, 10/10, I see the sign in button that I can click on.
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | JL, 10/10 I see the sign in button that I can click on. And I can create my own user name and password
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | JL, 10/10 I was redirected to the homepage and my name was saved
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | MB, 10/10
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | JL, 10/10 I was redirected to the sign in page when I used someone else's username
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MB, 10/10
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MB, 10/10
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | CG/KV, 10/10
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | CG/KV, 10/10
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | CG/KV, 10/10
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | 10/27 MB/JL
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | JL, 10/10 I am unable to drop the piece
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | JL, 10/10 I am unable to drop the piece
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | JL, 10/10 It is droppable, but there is an error saying it was not implemented yet
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JL, 10/10 I see on the board my pieces are at the bottom
As a player, I want to sign out so that I can exit a game of checkers
As a player, I want to make a single move so that I can move and play across the board
As a player, I want to make a single jump move so that I can capture an opponents piece
As a player, I want to make a double jump move so that I can capture multiple opponent pieces
As a player, I want to be kinged so I can move and jump diagonally forward and backwards
As a player, I want to be assigned to a color so that I know what player I am
As a Player I want to know if another player has left the game so that I can play another game.
As a player, I want to forfeit so I can resign the game
As a spectator I want to login so that I can watch a game of webcheckers.
As a Player and Spectator I want to know who is watching the game so that I can see how many viewers are watching the game.
As a spectator I want to see want games are happening so that I can choose who to watch.